## Execution Summary
E-Commerce Manual Testing - Execution Summary
Test execution overview ¦ Manual functional testing
Execution Summary |  | Test Cases by Priority |  | Bug Severity |  | Module Coverage
Total Test Cases | 14 | Priority | Count | Severity | Count | Module | Tests
Passed | 14 | Critical | 1 | Critical | 0 | Authentication | 3
Failed | 0 | High | 8 | High | 1 | Cart | 2
Blocked | 0 | Medium | 5 | Medium | 1 | Checkout | 2
Pass Rate | 100% | Low | 0 | Low | 1 | Contact Us | 2
Bugs Reported | 3 |  |  |  |  | Products | 3
[6 empty] | Registration | 2
Key Findings
• 14 of 14 executed test cases passed.
• 3 bugs were recorded during testing.
• High severity bugs: 1. Critical bugs: 0.
• Main test coverage areas: Authentication, Registration, Products, Cart, Checkout, Contact Us.

## Test Plan
Test Plan | E-Commerce Manual Testing
Objective | Validate the main user journeys and identify functional defects.
Scope | Authentication, Registration, Products, Cart, Checkout, Contact Us
Testing Type | Manual Functional Testing
Test Deliverables | Test Cases, Bug Report, Execution Summary
Environment | Web Application
Overall Result | PASS

## Test Cases
Test Case ID | Module | Test Scenario | Precondition | Test Steps | Expected Result | Priority | Status
TC-001 | Authentication | Valid user login | Registered user exists | Enter valid email/password; click Login | User is logged in successfully | High | Pass
TC-002 | Authentication | Invalid password | Registered email exists | Enter valid email and wrong password; click Login | Clear error is displayed; login is rejected | High | Pass
TC-003 | Authentication | Empty login fields | Login page available | Leave fields empty; click Login | Required-field validation appears | Medium | Pass
TC-004 | Registration | Create new account | Registration page available | Enter valid data; submit | Account is created successfully | High | Pass
TC-005 | Registration | Existing email registration | Email already registered | Register with existing email | Duplicate registration is rejected | High | Pass
TC-006 | Products | View product list | Application accessible | Open Products page | Products and required information are displayed | High | Pass
TC-007 | Products | Search existing product | Products exist | Search for existing product | Matching product is displayed | Medium | Pass
TC-008 | Products | Search non-existing product | Products page available | Search invalid product | Clear no-results state is displayed | Medium | Pass
TC-009 | Cart | Add product to cart | Product available | Open product; click Add to Cart | Product appears in cart | High | Pass
TC-010 | Cart | Remove product from cart | Cart contains product | Open cart; remove product | Product is removed and totals update | High | Pass
TC-011 | Checkout | Checkout with valid data | Cart contains product | Enter valid checkout data; place order | Order is placed successfully | Critical | Pass
TC-012 | Checkout | Checkout with missing required data | Cart contains product | Leave required field empty; submit | Validation appears; order is not placed | High | Pass
TC-013 | Contact Us | Submit valid contact form | Contact page available | Enter valid data and submit | Message is submitted successfully | Medium | Pass
TC-014 | Contact Us | Missing contact data | Contact page available | Leave required fields empty; submit | Validation appears | Medium | Pass

## Bug Rebort
Bug ID | Module | Title | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status
BUG-001 | Authentication | Invalid credentials show unclear error message | Medium | High | Enter invalid credentials and click Login | Clear authentication error | Feedback is unclear/inconsistent | Open
BUG-002 | Products | Invalid search shows unclear empty state | Low | Medium | Search for non-existing keyword | Clear no-results message/state | Empty result lacks guidance | Open
BUG-003 | Checkout | Required-field validation is inconsistent | High | High | Leave required checkout field empty and submit | Clear validation on the field | Validation is inconsistent | Open